FINAL REPORT

HealthConnect Analytics Project

Week 8 – Final Integration | AnalystLab Africa

# 1. Project Summary

HealthConnect has a 48.46% no-show rate. We built a predictive risk model to flag high-risk patients and propose targeted interventions.

# 2. What We Did From Week 4 to Week 7

## Week 4 – Cleaning

- 73% → 100% completeness

- Fixed 1,350 missing reminders, standardized gender/age, removed 4.8% duplicates

- Initial finding: Mondays and No Reminder channel are red flags

## Week 5 – EDA Bins

- Lead time 30+ days = 1,467 no-shows = 64% rate (biggest driver)

- Prior no-shows 2+ = 324 no-shows = 63% rate

- Distance 20+ km = 227 no-shows = 60% rate

- Finding: No-show is not only distance

## Week 6 – Built Product in Power BI

- 3 Measures: Total Appointments, No-Shows, No-Show Rate

- 1 Calculated Column: Risk Level = SWITCH (TRUE (), …)

- Output: patient_risk_segments table

- Validation: Low Risk 372 @ 21.77%, Medium 1,905 @ 37.85%, High 2,723 @ 59.53%

- 2.7x lift between Low and High = model works

## Week 7 – Testing & Refinement

- Tested Risk V2 on Mobile Clinic (30km+)

- Result: Critical 20 @ 60.00%, High 193 @ 70.98%, Total 213 @ 69.95%

- Card visual: Count appointment_id = 213 (validates pipeline)

- Refinement: Transport for 20–30km, Mobile Clinic for 30km+ (213 patients). Priority is the 193 High Risk patients.

# 3. Week 8 – Final Integration (This Week)

No new dashboard. Week 8 is packaging Week 7 for handoff.

## Engineering Handoff

- Implement SWITCH logic at booking to avoid 30+ day lead time for High Risk patients

- patient_risk_segments table is ready

## Product Handoff – Final Rules

| Risk Level | Count | No-Show Rate | Intervention |
| --- | --- | --- | --- |
| Low | 372 | 21.77% | 7-day SMS |
| Medium | 1,905 | 37.85% | 2-day reminder + confirmation |
| High | 2,723 | 59.53% | 2-day call. +20–30km: transport voucher. 30km+: Mobile Clinic |
| Mobile Clinic (30km+) | 213 | 69.95% | CHW visit + same-day reminder |

## Validation

- Week 7 group 69.95% vs Week 6 overall 48.46% = +21.49% improvement

- Proves the combined model (lead time + prior no-shows + distance) outperforms distance alone

## Lesson Learned

- Distance was tested in the SWITCH logic but didn't split cleanly, so it was kept as a targeting overlay instead

# 4. Impact & Next Steps

- If we reduce no-shows by 50% on the 213 Mobile Clinic patients, we recover approximately 107 appointments

- Monitoring: track Mobile Clinic no-show rate weekly against the 69.95% baseline

- V3 roadmap: add seasonality, day-of-week effects, and A/B testing of SMS timing